## Sheet1
Task ID | Task Name | Task Owner | Start Date | Due Date | Status | Comments
1 | Data Dictionary | Mackenzie Williams | 2026-09-13 | 2026-09-13 | Completed | Updating data dictionary
2 | Exception Failure Path | Clyde Orehuela | 2026-09-13 | 2026-09-13 | Completed | Updating exception failure path
3 | Short Responsibility Notes | Hailey Do | 2026-09-13 | 2026-09-13 | Completed | Updating short responsibility notes
4 | State Definitions | Hailey Do | 2026-09-13 | 2026-09-13 | Completed | Updating state definitions
5 | State Transition Diagram | Satya Dwiputranto | 2026-09-13 | 2026-09-13 | Completed | Updating diagram
6 | Three Tier Architecture | Andrea Esparza | 2026-09-13 | 2026-09-13 | Completed | Updating three tier architecture
7 | Transaction Workflow Diagram | Evan Flett | 2026-09-13 | 2026-09-13 | Completed | Updating transaction workflow diagram
8 | Check that HTML+CSS remain correct | Clyde, Satya, and Mackenzie | 2026-10-04 | 2026-10-05 | Completed | Checking that HTML+CSS are correct in the system
9 | Make sure externam app.js is connected | Satya Dwiputranto | 2026-10-16 | 2026-10-18 | Completed | Checking that externam app.js is connected
10 | One DOM selection + one event | Clyde and Satya | 2026-10-16 | 2026-10-18 | Completed | Creating one DOM selection+one event
11 | One project specific function | Mackenzie and Hailey | 2028-10-16 | 2026-10-18 | Completed | Creating one project specific function
12 | One visible page update | Evan Flett | 2026-10-17 | 2026-10-18 | Completed | Making sure to have one visible page update
13 | Three tested cases including a boundary | Evan, Andrea, Satya, and Hailey | 2026-10-18 | 2026-10-18 | Completed | tested 3 cases including a boundary
14 | Backend Testing | Satya Dwiputranto | 2026-10-18 | 2026-10-18 | Completed | Checking that reward system is functioning regarding points earned per transaction
15 | Adjusted Documents | Mackenzie and Satya | 2026-10-05 | Ongoing | Ongoing | Consistently adjusted documents to reflect recent changes
16 | Consistently Update CSS | Satya, Clyde, Mackenzie | 2026-09-27 | Ongoing | Ongoing | Consistently adjusted CSS document to provide better appearance and flare